## 送测进展
整改项 | 责任人 | 问题单(问题单数/已经解决问题单数) |  | 代码排查完成进度 | 完成时间 | 工作内容 | 风险模块
DataPipelineClient | 韩正晶 | 5 | 2 | 60% | 2017-10-13 | 1、排查重点 2、AppScan扫描发现和DSPortal有关，参考画像 | 是
DataPipelineService | 韩正晶 | 0 | 0 | 60% | 2017-10-13 | 1、排查重点 2、AppScan扫描发现和DSPortal有关，参考画像 | 是
Cryptutil | 韩正晶 | 0 | 0 | 100% | 2017-10-09 | 1、进行排查中
Dataload | 韩正晶 | 0 | 0 | 100% | 2017-10-09 | 1、进行排查中
ETL_lib/DataPush | 韩正晶 | 0 | 0 | 100% | 2017-10-09 | 1、进行排查中
HIBI_Export | 韩正晶 | 0 | 0 | 100% | 2017-10-09 | 1、进行排查中
flumeConfiguration | 韩正晶 | 0 | 0 | 100% | 2017-10-09 | 1、进行排查中
newDatatrandform | 韩正晶 | 0 | 0 | 100% | 2017-10-09 | 1、进行排查中
HIBI_ExecuteShell | 史习云 | 1 | 1 | 100% | 2017-10-09 | 1、进行排查中
Tools | 史习云 | 0 | 0 | 100% | 2017-10-09 | 1、未开始
TaskContralCenter | 史习云 | 34 | 33 | 100% | 2017-10-09 | 1、问题单修改 2、在送测版本上合代码 3、修改TCC审计日志，目前问题比较大 | 是
BI_UDF | 刘青 | 1 | 1 | 100% | 2017-10-09 | 1、已梳理完整改范围，进行整改中，目前问题比较大 | 是
EUI_HiAnalytics | 刘青 | 0 | 0 | 100% | 2017-10-09 | 1、安全整改完成
安全文档(新增、去掉) | 赵金涛 |  |  | 80% | 2017-10-09
刘青负责部件转测文档 | 刘青 |  |  | 80% | 2017-10-09
韩正晶负责部件转测文档(新增、去掉) | 韩正晶 |  |  | 60% | 2017-10-09
史习云负责部件转测文档(新增、去掉) | 史习云 |  |  | 60% | 2017-10-09
送测文档整合 | 史习云 |  |  | 80% | 2017-10-09
刘青负责部件安装包 | 刘青 |  |  | 100% | 2017-10-09
韩正晶负责部件安装包 | 韩正晶 |  |  | 70% | 2017-10-09
史习云负责部件安装包 | 史习云 |  |  | 100% | 2017-10-09
第三方开源认证(新增openssl 1.0.2k和openssh 7.4p1) | 王哲 |  |  | 70% | 2017-10-09
通信矩阵 | 史习云 |  |  | 0% | 2017-10-09
测试环境安全加固，补丁 | 林啸明 |  |  | 100% | 2017-10-09
测试环境检查清理 | 林啸明 |  |  | 0% | 2017-10-20
建立一个新的分支提交代码 | 史习云 |  |  | 100% | 2017-10-02
openssl安装目录下存在过多疑似无用秘钥，需要清理环境 | 林啸明 |  |  | 100% | 2017-10-10
appscan问题找wiseoper确认 | 韩正晶 |  |  | 100% | 2017-10-10
平台备案汇总 | 史习云 |  |  | 100% | 2017-10-10
冷备接入祥云 | 韩正晶 |  |  | 50% | 2017-10-13
各业务版本准备一个说明文档，只包括本次送测范围的业务说明，能解释清楚即可 | 史习云 |  |  | 0% | 2017-10-15
所有本次未送测部件给出详细安全整改的计划和进展 | 张政勇 |  |  | 50% | 2017-10-13
OpenDS安全整改 | 陈由峰 |  |  | 30% | 2017-10-31

## 问题单
业务模块 | 问题单总数 | 已关闭
TCC | 34 | 34
Data_Agent | 8 | 8
DataPipeline | 5 | 2
UDF | 1 | 1
合计 | 48 | 45
Ticket No. | 业务模块 | Ticket Status | Severity | Brief | Current Handler | 是否已关闭 | 备注
DTS2017082306415 | TCC | Root Cause Analysis | Minor | 【SDV1】【设计类-认证问题和会话管理-会话建立无限制机制】【TCC管理员修改密码后没有登出并清除会话信息，推荐做法变更密码的场景下需要清除服务端的会话，用户重新登录。】 | yanjuzhao WX406473 | Closed
DTS2017090811238 | TCC/DataGateway/UDF | Root Cause Analysis | Minor | 【安全测试】【数据平台】【BigData Platform 2.0.4.300】【国内版本】【非合规类--一般】正则表达式通过工具regexfuzzer进行检测 | luxiansheng WX504495 | Closed
DTS2017092708652 | TCC | Root Cause Review | Major | 【大数据平台-SDV1】【编码类-不正确输入校验-路径遍历和等价错误-一般】【白盒】TCC中 函数 exportRemoteShellLog未对taskId参数做任何校验直接用来拼接下载 | shixiyun 00359263 | Closed
DTS2017091809759 | TCC | Root Cause Review | Minor | 【数据平台-SDV2】【编码类-不良代码质量-工具扫描告警清理-一般】【工具扫描】数据平台TCC管理台AppScan 扫描存在中、低级风险 | yanjuzhao WX406473 | Closed
DTS2017093005890 | TCC | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【TCC_安全问题】【liuyapeng/wx385350】TCC可以通过密码修改功能，修改其它帐户密码 | shixiyun 00359263 | Closed
DTS2017093005476 | TCC | Root Cause Analysis | Suggestion | 【BigData Platform 2.0.4.301】【TCC_安全问题】【raojie/wx505640】系统对帐户的锁定时长不可配置，DOS攻击用户账户，业务用户不能长期被锁定，导致业务不可用 | shixiyun 00359263 | Closed
DTS2017093005349 | TCC | Root Cause Analysis | Suggestion | 【BigData Platform 2.0.4.301】【TCC_安全问题】【raojie/wx505640】验证码不为单一图 | shixiyun 00359263 | Closed | 问题定位中
DTS2017093004766 | TCC | Root Cause Analysis | Suggestion | 【BigData Platform 2.0.4.301】【TCC_安全问题】【raojie/wx505640】管理员重置用户口令（如：找回密码功能）后，用户登录系统时是否没有提示修改重置口令 | shixiyun 00359263 | Closed | 需要咨询安全组
DTS2017093004562 | TCC | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【TCC_功能问题】【liuyapeng/wx385350】TCC中的普通管理-任务管理页面，无法删除任务（数据删除提示失败） | shixiyun 00359263 | Closed
DTS2017093004350 | TCC | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【TCC_安全问题】【raojie/wx505640】且日志记录不完善，不能支撑事后审计。 | shixiyun 00359263 | Closed | 需要咨询安全组
DTS2017093004279 | TCC | Root Cause Analysis | Major | 【BigData Platform 2.0.4.301】【TCC_安全问题】【raojie/wx505640】登出无记录、自动锁定，解锁，强制用户下线，操作失败无审计日志 | shixiyun 00359263 | Closed
DTS2017093004226 | TCC | Root Cause Analysis | Suggestion | 【BigData Platform 2.0.4.301】【TCC_安全问题】【liuyapeng/wx385350】包含不安全的HTTP方法（如MOVE、COPY） | shixiyun 00359263 | Closed
DTS2017093003520 | TCC | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【TCC_安全问题】【liuyapeng/wx385350】重定向检查-跳转请求在服务器端没有白名单校验 | shixiyun 00359263 | Closed | 需要和提单人确认
DTS2017093002932 | TCC | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【TCC_安全问题】【liuyapeng/wx385350】基于 DOM 的跨站脚本有XSS注入 | shixiyun 00359263 | Closed | 需要和提单人确认
DTS2017093002710 | TCC | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【TCC_安全问题】【liuyapeng/wx385350】存储式跨站脚本有XSS注入 | shixiyun 00359263 | Closed | 需要和提单人确认
DTS2017093002492 | TCC | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【TCC_安全问题】【liuyapeng/wx385350】 反射式跨站脚本XSS注入 | shixiyun 00359263 | Closed | 需要和提单人确认
DTS2017093001847 | TCC | Root Cause Analysis | Major | 【BigData Platform 2.0.4.301】【TCC_安全问题】【raojie/wx505640】可通过认证失败提示信息进行用户猜测与用户枚举。 | xudongchen WX316829 | Closed
DTS2017092909131 | DataPipeline | Root Cause Analysis | Minor | 【N】【服务端】【安全测试】【DataPipeline】appscan扫描发现问题需分析解决 | tangfuqing WX440306 | Open
DTS2017092908659 | DataPipeline | Root Cause Analysis | Major | 【N】【服务端】【安全测试】【DataPipeline】DataPipelineService操作页面发现纵向越权。 | tangfuqing WX440306 | Open
DTS2017092908571 | DataPipeline | Root Cause Analysis | Minor | 【N】【服务端】【安全测试】【DataPipeline】DataPipelineService未发现有相关防csrf机制 | tangfuqing WX440306 | Open
DTS2017092908508 | DataPipeline | Root Cause Analysis | Minor | 【N】【服务端】【安全测试】【DataPipeline】开放HTTP方法测试，未对move\copy两个不安全的HTTP方法方法进行屏蔽 | tangfuqing WX440306 | Open
DTS2017092708417 | TCC | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【TCC_安全问题】【liuyapeng/wx385350】TCC日志级别设置不合理 | shixiyun 00359263 | Closed
DTS2017092703367 | TCC | Root Cause Analysis | Major | 【BigData Platform 2.0.4.301】【TCC_安全问题】【liuyapeng/wx385350】TCC日志记录不完善 | shixiyun 00359263 | Closed
DTS2017091806198 | DataPipeline | Root Cause Analysis | Minor | 【BigData Platform 2.0.4.301】【DataPipeline_安全问题】【liuyapeng/wx385350】系统的根密钥生成方式不合规 | tangfuqing WX440306 | Open
DTS2017090706141 | UDF | Root Cause Review | Minor | 【BigData Platform 2.0.4.301】【UDF_安全问题】【liuyapeng/wx385350】UDF函数为了兼容业务历史数据，存在多处符合安全要求的加密算法，iv等，需与业务进行联合整改 | liuqing 00194648 | Open
DTS2017082802953 | TCC | Solution Implementation | Major | 计算资源利用不合理集中在0:0-2:00 6:00-8:00区间，中间较空计算任务调度有较大优化空间。 | shixiyun 00359263 | Open
DTS2017072806748 | MFS | Root Cause Analysis | Minor | 【BI】【功能优化】润泽MFS读写速率、MFS CGI监控页面响应很慢 | liuqing 00194648 | Open
DTS2017070400253 | Datapush | Root Cause Review | Minor | 【N】【服务端】【SDV】【海外版本】【Datapush_数据入库】datapush推送超时，导致香港PSI文件延迟原因。 | lvliang WX482252 | Open
DTS2017100600905 | TCC | Ticket Review | Major | [Vulnerability][Dispatch] Apache Struts 2.3.32 has security vulnerabilities, including 2 records. | linxiaoming 00216915,qiucaixiu 00196442 | Closed
DTS2017100600886 | TCC | Ticket Review | Major | [Vulnerability][Dispatch] Apache Struts 2.3.33 has security vulnerabilities, including 2 records. | linxiaoming 00216915,qiucaixiu 00196442 | Closed
DTS2017100600846 | TCC | Ticket Review | Major | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 2 records. | linxiaoming 00216915,qiucaixiu 00196442 | Closed
DTS2017100600845 | TCC | Ticket Review | Major | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 2 records. | linxiaoming 00216915,qiucaixiu 00196442 | Closed
DTS2017092900165 | Data_Agent | Root Cause Analysis | Major | [Vulnerability][Dispatch] Spring Boot 1.3.2.RELEASE has security vulnerabilities, including 1 records. | shixiyun 00359263 | Open | 需要各模块责任人确认
DTS2017092900160 | Data_Agent | Root Cause Analysis | Major | [Vulnerability][Dispatch] Spring Boot 1.3.2.RELEASE has security vulnerabilities, including 1 records. | shixiyun 00359263 | Open | 需要各模块责任人确认
DTS2017092900137 | Data_Agent | Root Cause Analysis | Major | [Vulnerability][Dispatch] Spring Boot 1.3.2.RELEASE has security vulnerabilities, including 1 records. | shixiyun 00359263 | Open | 需要各模块责任人确认
DTS2017092900121 | Data_Agent | Root Cause Analysis | Major | [Vulnerability][Dispatch] Spring Boot 1.3.2.RELEASE has security vulnerabilities, including 1 records. | shixiyun 00359263 | Open | 需要各模块责任人确认
DTS2017092702586 | Data_Agent | Root Cause Analysis | Critical | [Vulnerability][Dispatch] Spring Boot 1.3.2.RELEASE has security vulnerabilities, including 1 records. | liyue 00354527 | Open | 需要各模块责任人确认
DTS2017092702582 | Data_Agent | Root Cause Analysis | Critical | [Vulnerability][Dispatch] Spring Boot 1.3.2.RELEASE has security vulnerabilities, including 1 records. | liyue 00354527 | Open | 需要各模块责任人确认
DTS2017092702550 | Data_Agent | Root Cause Analysis | Critical | [Vulnerability][Dispatch] Spring Boot 1.3.2.RELEASE has security vulnerabilities, including 1 records. | shixiyun 00359263 | Open | 需要各模块责任人确认
DTS2017092702531 | Data_Agent | Root Cause Analysis | Critical | [Vulnerability][Dispatch] Spring Boot 1.3.2.RELEASE has security vulnerabilities, including 1 records. | shixiyun 00359263 | Open | 需要各模块责任人确认
DTS2017092301030 | TCC | Root Cause Analysis | Critical | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 1 records. | xudongchen WX316829 | Closed
DTS2017092301026 | TCC | Root Cause Analysis | Critical | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 1 records. | xudongchen WX316829 | Closed
DTS2017092012550 | TCC | Root Cause Analysis | Major | [Vulnerability][Dispatch] Apache Struts 2.3.33 has security vulnerabilities, including 1 records. | xudongchen WX316829 | Closed
DTS2017092012509 | TCC | Root Cause Analysis | Major | [Vulnerability][Dispatch] Apache Struts 2.3.32 has security vulnerabilities, including 1 records. | xudongchen WX316829 | Closed
DTS2017091109365 | TCC | Solution Implementation | Major | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 2 records. | xudongchen WX316829 | Closed
DTS2017091109364 | TCC | Root Cause Analysis | Major | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 2 records. | xudongchen WX316829 | Closed
DTS2017090804694 | TCC | Root Cause Analysis | Major | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 1 records. | xudongchen WX316829 | Closed
DTS2017090804693 | TCC | Root Cause Analysis | Major | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 1 records. | xudongchen WX316829 | Closed
DTS2017090604852 | TCC | Root Cause Review | Critical | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 1 records. | xudongchen WX316829 | Closed
DTS2017090604850 | TCC | Root Cause Analysis | Critical | [Vulnerability][Dispatch] Apache Struts 2.3.30 has security vulnerabilities, including 1 records. | xudongchen WX316829 | Closed

## 文档编写责任人
文档名称 | 责任人 | 完成状态
安全配置-加固指南 | 史习云，找啸鸣协助一下
安全隐私top问题自检 | 史习云、韩正晶、刘青(金涛2017/10/10组织一下)
代码安全检视报告 | 史习云、韩正晶、刘青
差异化分析说明书 | 史习云、韩正晶、刘青
代码静态扫描报告 | 史习云、韩正晶、刘青，从流水线获取
AppScan扫描报告 | 史习云，韩正晶
通信矩阵 | 史习云，韩正晶、刘青
第三方开源认证报告 | 王哲
开源及第三方软件使用申请单 | 王哲
安全打分自检 | 史习云
云服务部署运营隐私及安全合规策略 | 史习云
CBG隐私保护及网络安全-基于GAPP框架Checklist | 史习云
数据处理文档 | 史习云
个人数据定义 | 史习云
woodpecker扫描报告 | 各个负责人归包，刘亚鹏扫描
开发自测报告 | 史习云、韩正晶、刘青
性能测试报告 | 林啸明
测试建议 | 史习云、韩正晶、刘青
BigData Platform 2.0.4.302 自测报告.xlsx | 史习云